## Table 1
ORDER STATUS AND DISPATCH SCHEDULE- Sept 2026
| Customer/ OA Reference | Product | Order Status | Payment Status | Invoice status | Dispatch schedule | Site Status/ Remark
1 | Nilkanth OA 04 | ALPHA 1500 | Confirmed | Part payment received | Issued | Sept. | Erection Started Part dispatch
2 | Someshawar OA 09 | DELTA 100 | Confirmed | Major payment Received | Issued | Dispatched | Plant under trial Production
3 | Abhishesk OA 13 | DELTA 100 | Confirmed | Full Payment received | Issued | Sept | Foundation done. Dispatch Started
4 | Gua & Roy OA 14 | ALPHA 1500 | Confirmed | Full payment Received | Issued | Sept- Oct | Part load dispatched
5 | Dhotre. MH OA 16 | ALPHA 1500 | Confirmed | Payment received | issued | Sept-Oct | Foundation is almost done. Dispatch Started
6 | RR Ent OA 03 | AF4500 | Confirmed | Full Payment | Yes | Dispatched | Under Commissioning
7 | DEO HRADAY | AF4500 | Confirm Order | Advance Received | NO | Oct | Waiting for Balance Payment
8 | Arasu- TN | AF4500 | Confirm Order | Advance Received | NO | Oct | Waiting for Balance Payment
9 | Navodaya- AP | AF4500 | Confirm order | Advance received | No | Oct | Waiting for Balance Payment
10 | Ram Eng - AP | AF4500 | Confirm order | Advance received | No | Oct | Waiting for Balance Payment
11 | Jay Bhawani- Guj | AF4500 | Confirm Order | Advance Received | No | Oct | Waiting for Balance Payment
12 | Pannu Construction Punjab | AF4500 | Confirm order | Advance Received | No | Oct | Waiting for Balance Payment